## Sheet1
Task / Subtask |  |  | Comment | Min | Real | Max | Avg | SD | Sq
Stage 1: Implement the Idea | 0 |  | use MindMaps in estimation process
Define the Idea | 0
Look for samples | 1 |  |  | 1 | 1 | 2 | 1.1667 | 0.16667 | 0.027778
Determine report structure | 1 |  |  | 1 | 2 | 4 | 2.1667 | 0.5 | 0.25
Determine translation rules | 1 |  |  | 1 | 2 | 4 | 2.1667 | 0.5 | 0.25
Look for Math | 1 |  |  | 0 | 1 | 3 | 1.1667 | 0.5 | 0.25
Choose a MindMap editor | 1 |  |  | 1 | 2 | 5 | 2.3333 | 0.66667 | 0.44444
Code it | 0
Choose a language/libs | 1 |  |  | 1 | 1 | 2 | 1.1667 | 0.16667 | 0.027778
Implementation | 1 |  |  | 2 | 3 | 5 | 3.1667 | 0.5 | 0.25
Check it with example project | 1 |  |  | 1 | 1 | 2 | 1.1667 | 0.16667 | 0.027778
Stage 2: Proof the approach | 0 |  | probe the approach with projects
Proof it with test projects | 1 |  |  | 1 | 3 | 5 | 3 | 0.66667 | 0.44444
Real life testing | 0 |  | find somewhere real projects, test how it works
Proof it with real projects | 1 |  |  | 3 | 5 | 10 | 5.5 | 1.1667 | 1.3611
Documentation | 1 |  |  | 2 | 2 | 3 | 2.1667 | 0.16667 | 0.027778
Feedback analysis | 1 |  |  | 1 | 2 | 2 | 1.8333 | 0.16667 | 0.027778
Improvements | 1 |  |  | 0 | 4 | 7 | 3.8333 | 1.1667 | 1.3611
Stage 3: Share it | 0 |  | make it available
Publish it on GitHub | 1 |  |  | 1 | 1 | 2 | 1.1667 | 0.16667 | 0.027778
Clean up the code | 0
Code structure & Comments | 1 |  |  | 1 | 2 | 5 | 2.3333 | 0.66667 | 0.44444
Tests | 1 |  |  | 2 | 3 | 5 | 3.1667 | 0.5 | 0.25
Document the approach | 1 |  |  | 2 | 4 | 5 | 3.8333 | 0.5 | 0.25
End user tool documentation | 1 |  |  | 1 | 1 | 2 | 1.1667 | 0.16667 | 0.027778
Ask for feedback | 1 |  | ask someone I knew for feedback | 1 | 1 | 2 | 1.1667 | 0.16667 | 0.027778
Stage 4: Improve it | 0 |  | make it useful
Look for feedback | 1 |  |  | 2 | 3 | 5 | 3.1667 | 0.5 | 0.25
Analyze feedbacks | 1 |  |  | 2 | 5 | 8 | 5 | 1 | 1
Improvements | 1 |  |  | 0 | 5 | 15 | 5.8333 | 2.5 | 6.25
Total |  |  |  | 27 | 54 | 103 | 57.6667 | 12.6667 | 13.2778
Standard deviation |  | 3.6439
K |  | 1.5
Min (P=99%) |  | 46.7351 | 70.1026
Min (P=99%) |  | 68.5983 | 102.8974