## Estimates
Task / Subtask | Filter | MVP | Comment | Min | Real | Max | Avg | SD | Sq
Stage 1: Implement the Idea |  |  | use MindMaps in estimation process
Define the Idea
Look for samples | 1 | 1 |  | 1 | 1 | 2
Determine report structure | 1 | 1 |  | 1 | 2 | 4
Determine translation rules | 1 | 1 |  | 1 | 2 | 4
Look for Math | 1 | 1 |  | 0 | 1 | 3
Code it
Choose a language/libs | 1 | 1 |  | 1 | 1 | 2
Implementation | 1 | 1 |  | 2 | 3 | 5
Choose a MindMap editor | 1 | 1 |  | 1 | 2 | 5
Check it with example project | 1 | 1 |  | 1 | 1 | 2
Stage 2: Proof the approach |  |  | probe the approach with projects
Real life testing |  |  | find somewhere real projects, test how it works
Proof it with real projects | 1 | 1 |  | 3 | 5 | 10
Documentation | 1 | 1 |  | 2 | 2 | 3
Feedback analysis | 1 | 1 |  | 1 | 2 | 2
Proof it with test projects | 1 | 1 |  | 1 | 3 | 5
Improvements | 1 | 1 |  | 0 | 4 | 7
Stage 3: Share it |  |  | make it available
Clean up the code
Code structure & Comments | 1 | 1 |  | 1 | 2 | 5
Tests | 1 | 1 |  | 2 | 3 | 5
Publish it on GitHub | 1 | 1 |  | 1 | 1 | 2
Document the approach | 1 | 1 |  | 2 | 4 | 5
End user tool documentation | 1 | 1 |  | 1 | 1 | 2
Ask for feedback | 1 | 1 | ask someone I knew for feedback | 1 | 1 | 2
Stage 4: Improve it |  |  | make it useful
Look for feedback | 1 | 1 |  | 2 | 3 | 5
Analyze feedbacks | 1 | 1 |  | 2 | 5 | 8
Improvements | 1 | 1 |  | 0 | 5 | 15
Total
Total (MVP)
Standard deviation
K |  | 1.5
Min (P=99%)
Max (P=99%)