## Sheet1
Task / Subtask |  |  | Comment | Min | Real | Max | Avg | SD | Sq | (adm) | (analysis) | (coding)
Stage 1: Implement the Idea | 0 |  | use MindMaps in estimation process
Define the Idea | 0
Look for samples | 1 |  |  | 1 | 1 | 2 | 0 | 0 | 0
(analysis) | 0 |  |  | 1 | 1 | 2 |  |  |  |  | 1
Determine report structure | 1 |  |  | 1 | 2 | 4 | 0 | 0 | 0
(analysis) | 0 |  |  | 1 | 2 | 4 |  |  |  |  | 1
Determine translation rules | 1 |  |  | 1 | 2 | 4 | 0 | 0 | 0
(analysis) | 0 |  |  | 1 | 2 | 4 |  |  |  |  | 1
Look for Math | 1 |  |  | 0 | 1 | 3 | 0 | 0 | 0
(analysis) | 0 |  |  | 0 | 1 | 3 |  |  |  |  | 1
Choose a MindMap editor | 1 |  |  | 1 | 2 | 5 | 0 | 0 | 0
(analysis) | 0 |  |  | 1 | 2 | 5 |  |  |  |  | 1
Code it | 0
Choose a language/libs | 1 |  |  | 1 | 1 | 2 | 0 | 0 | 0
(coding) | 0 |  |  | 1 | 1 | 2 | [5 empty] | 1
Implementation | 1 |  |  | 2 | 3 | 5 | 0 | 0 | 0
(coding) | 0 |  |  | 2 | 3 | 5 | [5 empty] | 1
Check it with example project | 1 |  |  | 1 | 1 | 2 | 0 | 0 | 0
(analysis) | 0 |  |  | 1 | 1 | 2 |  |  |  |  | 1
Stage 2: Proof the approach | 0 |  | probe the approach with projects
Proof it with test projects | 1 |  |  | 1 | 3 | 5 | 0 | 0 | 0
(analysis) | 0 |  |  | 1 | 2 | 2 |  |  |  |  | 1
(coding) | 0 |  |  | 0 | 1 | 3 | [5 empty] | 1
Real life testing | 0 |  | find somewhere real projects, test how it works
Proof it with real projects | 1 |  |  | 3 | 5 | 10 | 0 | 0 | 0
(analysis) | 0 |  |  | 3 | 5 | 10 |  |  |  |  | 1
Documentation | 1 |  |  | 2 | 2 | 3 | 0 | 0 | 0
(analysis) | 0 |  |  | 2 | 2 | 3 |  |  |  |  | 1
Feedback analysis | 1 |  |  | 1 | 2 | 2 | 0 | 0 | 0
(analysis) | 0 |  |  | 1 | 2 | 2 |  |  |  |  | 1
Improvements | 1 |  |  | 0 | 4 | 7 | 0 | 0 | 0
(analysis) | 0 |  |  | 0 | 1 | 2 |  |  |  |  | 1
(coding) | 0 |  |  | 0 | 3 | 5 | [5 empty] | 1
Stage 3: Share it | 0 |  | make it available
Publish it on GitHub | 1 |  |  | 1 | 1 | 2 | 0 | 0 | 0
(adm) | 0 |  |  | 1 | 1 | 2 |  |  |  | 1
Clean up the code | 0
Code structure & Comments | 1 |  |  | 1 | 2 | 5 | 0 | 0 | 0
(coding) | 0 |  |  | 1 | 2 | 5 | [5 empty] | 1
Tests | 1 |  |  | 2 | 3 | 5 | 0 | 0 | 0
(coding) | 0 |  |  | 2 | 3 | 5 | [5 empty] | 1
Document the approach | 1 |  |  | 2 | 4 | 5 | 0 | 0 | 0
(analysis) | 0 |  |  | 2 | 4 | 5 |  |  |  |  | 1
End user tool documentation | 1 |  |  | 1 | 1 | 2 | 0 | 0 | 0
(analysis) | 0 |  |  | 1 | 1 | 2 |  |  |  |  | 1
Ask for feedback | 1 |  | ask someone I knew for feedback | 1 | 1 | 2 | 0 | 0 | 0
(analysis) | 0 |  |  | 1 | 1 | 2 |  |  |  |  | 1
Stage 4: Improve it | 0 |  | make it useful
Look for feedback | 1 |  |  | 2 | 3 | 5 | 0 | 0 | 0
(analysis) | 0 |  |  | 2 | 3 | 5 |  |  |  |  | 1
Analyze feedbacks | 1 |  |  | 2 | 5 | 8 | 0 | 0 | 0
(analysis) | 0 |  |  | 2 | 5 | 8 |  |  |  |  | 1
Improvements | 1 |  |  | 0 | 5 | 15 | 0 | 0 | 0
(coding) | 0 |  |  | 0 | 5 | 15 | [5 empty] | 1
Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
- adm |  |  |  | 0 | 0 | 0
- analysis |  |  |  | 0 | 0 | 0
- coding |  |  |  | 0 | 0 | 0
Standard deviation |  | 0
K |  | 1.5
Min (P=95%) |  | 0 | 0
Min (P=95%) |  | 0 | 0