## Estimates
Task / Subtask | Filter |  | Comment | Min | Real | Max | Avg | SD | Sq | (adm) | (analysis) | (coding) | (test)
Stage 1: Implement the Idea |  |  | use MindMaps in estimation process | 8 | 13 | 27
Define the Idea |  |  |  | 3 | 6 | 13
Look for samples | 1 |  |  | 1 | 1 | 2 | 1.1667 | 0.16667 | 0.027778
(analysis) | 0 |  |  | 1 | 1 | 2 |  |  |  |  | 1
Determine report structure | 1 |  |  | 1 | 2 | 4 | 2.1667 | 0.5 | 0.25
(analysis) | 0 |  |  | 1 | 2 | 4 |  |  |  |  | 1
Determine translation rules | 1 |  |  | 1 | 2 | 4 | 2.1667 | 0.5 | 0.25
(analysis) | 0 |  |  | 1 | 2 | 4 |  |  |  |  | 1
Look for Math | 1 |  |  | 0 | 1 | 3 | 1.1667 | 0.5 | 0.25
(analysis) | 0 |  |  | 0 | 1 | 3 |  |  |  |  | 1
Code it |  |  |  | 3 | 4 | 7
Choose a language/libs | 1 |  |  | 1 | 1 | 2 | 1.1667 | 0.16667 | 0.027778
(coding) | 0 |  |  | 1 | 1 | 2 | [5 empty] | 1
Implementation | 1 |  |  | 2 | 3 | 5 | 3.1667 | 0.5 | 0.25
(coding) | 0 |  |  | 2 | 3 | 5 | [5 empty] | 1
Choose a MindMap editor | 1 |  |  | 1 | 2 | 5 | 2.3333 | 0.66667 | 0.44444
(analysis) | 0 |  |  | 1 | 2 | 5 |  |  |  |  | 1
Check it with example project | 1 |  |  | 1 | 1 | 2 | 1.1667 | 0.16667 | 0.027778
(analysis) | 0 |  |  | 1 | 1 | 2 |  |  |  |  | 1
Stage 2: Proof the approach |  |  | probe the approach with projects | 7 | 16 | 27
Real life testing |  |  | find somewhere real projects, test how it works | 6 | 9 | 15
Proof it with real projects | 1 |  |  | 3 | 5 | 10 | 5.5 | 1.1667 | 1.3611
(analysis) | 0 |  |  | 3 | 5 | 10 |  |  |  |  | 1
Documentation | 1 |  |  | 2 | 2 | 3 | 2.1667 | 0.16667 | 0.027778
(analysis) | 0 |  |  | 2 | 2 | 3 |  |  |  |  | 1
Feedback analysis | 1 |  |  | 1 | 2 | 2 | 1.8333 | 0.16667 | 0.027778
(analysis) | 0 |  |  | 1 | 2 | 2 |  |  |  |  | 1
Proof it with test projects | 1 |  |  | 1 | 3 | 5 | 3 | 0.66667 | 0.44444
(analysis) | 0 |  |  | 1 | 2 | 2 |  |  |  |  | 1
(coding) | 0 |  |  | 0 | 1 | 3 | [5 empty] | 1
Improvements | 1 |  |  | 0 | 4 | 7 | 3.8333 | 1.1667 | 1.3611
(analysis) | 0 |  |  | 0 | 1 | 2 |  |  |  |  | 1
(coding) | 0 |  |  | 0 | 3 | 5 | [5 empty] | 1
Stage 3: Share it |  |  | make it available | 8 | 12 | 21
Clean up the code |  |  |  | 3 | 5 | 10
Code structure & Comments | 1 |  |  | 1 | 2 | 5 | 2.3333 | 0.66667 | 0.44444
(coding) | 0 |  |  | 1 | 2 | 5 | [5 empty] | 1
Tests | 1 |  |  | 2 | 3 | 5 | 3.1667 | 0.5 | 0.25
(coding) | 0 |  |  | 2 | 3 | 5 | [5 empty] | 1
Publish it on GitHub | 1 |  |  | 1 | 1 | 2 | 1.1667 | 0.16667 | 0.027778
(adm) | 0 |  |  | 1 | 1 | 2 |  |  |  | 1
Document the approach | 1 |  |  | 2 | 4 | 5 | 3.8333 | 0.5 | 0.25
(analysis) | 0 |  |  | 2 | 4 | 5 |  |  |  |  | 1
End user tool documentation | 1 |  |  | 1 | 1 | 2 | 1.1667 | 0.16667 | 0.027778
(analysis) | 0 |  |  | 1 | 1 | 2 |  |  |  |  | 1
Ask for feedback | 1 |  | ask someone I knew for feedback | 1 | 1 | 2 | 1.1667 | 0.16667 | 0.027778
(analysis) | 0 |  |  | 1 | 1 | 2 |  |  |  |  | 1
Stage 4: Improve it |  |  | make it useful | 4 | 13 | 28
Look for feedback | 1 |  |  | 2 | 3 | 5 | 3.1667 | 0.5 | 0.25
(analysis) | 0 |  |  | 2 | 3 | 5 |  |  |  |  | 1
Analyze feedbacks | 1 |  |  | 2 | 5 | 8 | 5 | 1 | 1
(analysis) | 0 |  |  | 2 | 5 | 8 |  |  |  |  | 1
Improvements | 1 |  |  | 0 | 5 | 15 | 5.8333 | 2.5 | 6.25
(coding) | 0 |  |  | 0 | 5 | 15 | [5 empty] | 1
... |  |  | this is a temporary branch for theme testing | 0 | 0 | 0
... |  |  |  | 0 | 0 | 0
... |  |  |  | 0 | 0 | 0
... |  |  |  | 0 | 0 | 0
... |  |  |  | 0 | 0 | 0
... |  |  |  | 0 | 0 | 0
... |  |  |  | 0 | 0 | 0
... |  |  |  | 0 | 0 | 0
... | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0
(test) | 0 |  |  | 0 | 0 | 0 | [6 empty] | 1
... | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0
(test) | 0 |  |  | 0 | 0 | 0 | [6 empty] | 1
... |  |  |  | 0 | 0 | 0
... |  |  |  | 0 | 0 | 0
... |  |  |  | 0 | 0 | 0
... | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0
(test) | 0 |  |  | 0 | 0 | 0 | [6 empty] | 1
... |  |  |  | 0 | 0 | 0
... |  |  |  | 0 | 0 | 0
... | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0
(test) | 0 |  |  | 0 | 0 | 0 | [6 empty] | 1
Total |  |  |  | 27 | 54 | 103 | 57.6667 | 12.6667 | 13.2778
- adm |  |  |  | 1 | 1 | 2
- analysis |  |  |  | 20 | 35 | 61
- coding |  |  |  | 6 | 18 | 40
- test |  |  |  | 0 | 0 | 0
Standard deviation |  | 3.6439
K |  | 1.5
Min (P=95%) |  | 50.3789 | 75.5684
Max (P=95%) |  | 64.9544 | 97.4316